## Timeline
Start Date | Hours of per week | Estimated Date of Completion
Enter the date you started studying | Enter the number you will commit | Lower Bound | Upper Bound
2022-01-05 | 25 | 2023-01-14 10:34 | 2023-05-11 18:14

## Curriculum Data
Courses | Topic | Duration | Effort | Total Hours Lower Bound | Start Date | End Date Estimate Lower Bound | Total Hours Upper Bound | Start Date | End Date Estimate Upper Bound | Actual End Date | Prerequisites
Python for Everybody | Intro CS | 10 weeks | 10 hours/week | 100 | 2022-01-05 | 2022-01-05 | 100 | 2022-01-05 | 2022-01-05 | 2022-01-05 | -
Introduction to Computer Science and Programming using Python | Intro CS | 9 weeks | 15 hours/week | 135 | 2022-01-05 | 2022-01-07 | 135 | 2022-01-05 | 2022-01-07 | 2022-01-07 | high school algebra
How to Code - Simple Data | Core Programming | 7 weeks | 8-10 hours/week | 56 | 2022-01-07 | null | 70 | 2022-01-07 | null | null | -
How to Code - Complex Data | Core Programming | 6 weeks | 8-10 hours/week | 48 | null | null | 60 | null | null | null | How to Code: Simple Data
Programming Languages, Part A | Core Programming | 5 weeks | 4-8 hours/week | 20 | null | null | 40 | null | null | null | How to Code (Hear instructor)
Programming Languages, Part B | Core Programming | 3 weeks | 4-8 hours/week | 12 | null | null | 24 | null | null | null | Programming Languages, Part A
Programming Languages, Part C | Core Programming | 3 weeks | 4-8 hours/week | 12 | null | null | 24 | null | null | null | Programming Languages, Part B
Object-Oriented Design | Core Programming | 4 weeks | 4 hours/week | 16 | null | 2022-01-10 | 16 | null | 2022-01-10 | 2022-01-10 | Basic Java
Design Patterns | Core Programming | 4 weeks | 4 hours/week | 16 | 2022-01-10 | 2022-01-21 | 16 | 2022-01-10 | 2022-01-21 | 2022-01-21 | Object-Oriented Design
Software Architecture | Core Programming | 4 weeks | 2-5 hours/week | 8 | 2022-01-21 | 2022-01-23 | 20 | 2022-01-21 | 2022-01-23 | 2022-01-23 | Design Patterns
Calculus 1A: Differentiation | Core Math | 13 weeks | 6-10 hours/week | 78 | 2022-01-23 | 2022-02-13 20:10 | 130 | 2022-01-23 | 2022-02-28 09:36 |  | high school math
Calculus 1B: Integration | Core Math | 13 weeks | 5-10 hours/week | 65 | 2022-02-13 20:10 | 2022-03-04 00:58 | 130 | 2022-02-28 09:36 | 2022-04-05 19:12 |  | Calculus 1A
Calculus 1C: Coordinate Systems & Infinite Series | Core Math | 6 weeks | 5-10 hours/week | 30 | 2022-03-04 00:58 | 2022-03-12 10:34 | 60 | 2022-04-05 19:12 | 2022-04-22 14:24 |  | Calculus 1B
Mathematics for Computer Science | Core Math | 13 weeks | 5 hours/week | 65 | 2022-03-12 10:34 | 2022-03-30 15:22 | 65 | 2022-04-22 14:24 | 2022-05-10 19:12 |  | Calculus 1C
The Missing Semester of Your CS Education | CS Tools | 2 weeks | 12 hours/week | 24 | 2022-03-30 15:22 | 2022-04-06 08:38 | 24 | 2022-05-10 19:12 | 2022-05-17 12:29 |  | -
Build a Modern Computer from First Principles: From Nand to Tetris | Core Systems | 6 weeks | 7-13 hours/week | 42 | 2022-04-06 08:38 | 2022-04-18 02:53 | 78 | 2022-05-17 12:29 | 2022-06-08 08:38 |  | C-like programming language
Build a Modern Computer from First Principles: Nand to Tetris Part II | Core Systems | 6 weeks | 12-18 hours/week | 72 | 2022-04-18 02:53 | 2022-05-08 06:43 | 108 | 2022-06-08 08:38 | 2022-07-08 14:24 |  | one of these programming languages, From Nand to Tetris Part I
Operating Systems: Three Easy Pieces | Core Systems | 10-12 weeks | 6 hours/week | 60 | 2022-05-08 06:43 | 2022-05-25 01:55 | 72 | 2022-07-08 14:24 | 2022-07-28 18:14 |  | algorithms, familiarity with C is useful
Computer Networking: a Top-Down Approach | Core Systems | 8 weeks | 4-12 hours/week | 32 | 2022-05-25 01:55 | 2022-06-03 00:58 | 96 | 2022-07-28 18:14 | 2022-08-24 15:22 |  | algebra, probability, basic CS
Divide and Conquer, Sorting and Searching, and Randomized Algorithms | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-06-03 00:58 | 2022-06-07 12:29 | 32 | 2022-08-24 15:22 | 2022-09-02 14:24 |  | any programming language, Mathematics for Computer Science
Graph Search, Shortest Paths, and Data Structures | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-06-07 12:29 | 2022-06-12 | 32 | 2022-09-02 14:24 | 2022-09-11 13:26 |  | Divide and Conquer, Sorting and Searching, and Randomized Algorithms
Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-06-12 | 2022-06-16 11:31 | 32 | 2022-09-11 13:26 | 2022-09-20 12:29 |  | Graph Search, Shortest Paths, and Data Structures
Shortest Paths Revisited, NP-Complete Problems and What To Do About Them | Core Theory | 4 weeks | 4-8 hours/week | 16 | 2022-06-16 11:31 | 2022-06-20 23:02 | 32 | 2022-09-20 12:29 | 2022-09-29 11:31 |  | Greedy Algorithms, Minimum Spanning Trees, and Dynamic Programming
Information Security: Context and Introduction | Core Security | 5 weeks | 3 hours/week | 15 | 2022-06-20 23:02 | 2022-06-25 03:50 | 15 | 2022-09-29 11:31 | 2022-10-03 16:19 |  | -
Principles of Secure Coding | Core Security | 4 weeks | 4 hours/week | 16 | 2022-06-25 03:50 | 2022-06-29 15:22 | 16 | 2022-10-03 16:19 | 2022-10-08 03:50 |  | -
Identifying Security Vulnerabilities | Core Security | 4 weeks | 4 hours/week | 16 | 2022-06-29 15:22 | 2022-07-04 02:53 | 16 | 2022-10-08 03:50 | 2022-10-12 15:22 |  | -
Identifying Security Vulnerabilities in C/C++ Programming or Exploiting and Securing Vulnerabilities in Java Applications | Core Security | 4 weeks | 5 hours/week | 20 | 2022-07-04 02:53 | 2022-07-09 17:17 | 20 | 2022-10-12 15:22 | 2022-10-18 05:46 |  | -
Databases: Modeling and Theory | Core Applications | 2 weeks | 10 hours/week | 20 | 2022-07-15 07:41 | 2022-07-20 22:05 | 20 | 2022-10-23 20:10 | 2022-10-29 10:34 |  | core programming
Databases: Relational Databases and SQL | Core Applications | 2 weeks | 10 hours/week | 20 | 2022-07-09 17:17 | 2022-07-15 07:41 | 20 | 2022-10-18 05:46 | 2022-10-23 20:10 |  | core programming
Databases: Semistructured Data | Core Applications | 2 weeks | 10 hours/week | 20 | 2022-07-20 22:05 | 2022-07-26 12:29 | 20 | 2022-10-29 10:34 | 2022-11-04 00:58 |  | core programming
Machine Learning | Core Applications | 11 weeks | 4-6 hours/week | 44 | 2022-07-26 12:29 | 2022-08-07 20:10 | 66 | 2022-11-04 00:58 | 2022-11-22 12:29 |  | linear algebra
Computer Graphics | Core Applications | 6 weeks | 12 hours/week | 72 | 2022-08-07 20:10 | 2022-08-28 | 72 | 2022-11-22 12:29 | 2022-12-12 16:19 |  | C++ or Java, linear algebra
Software Engineering: Introduction | Core Applications | 6 weeks | 8-10 hours/week | 48 | 2022-08-28 | 2022-09-10 10:34 | 60 | 2022-12-12 16:19 | 2022-12-29 11:31 |  | Core Programming, and a sizable project
Parallel Programming | Advanced Programming | 4 weeks | 6-8 hours/week | 24 | 2022-09-10 10:34 | 2022-09-17 03:50 | 32 | 2022-12-29 11:31 | 2023-01-07 10:34 |  | Scala programming
Compilers | Advanced Programming | 9 weeks | 6-8 hours/week | 54 | 2022-09-17 03:50 | 2022-10-02 06:43 | 72 | 2023-01-07 10:34 | 2023-01-27 14:24 |  | none
Introduction to Haskell | Advanced Programming | 14 weeks | - | 100 | 2022-10-02 06:43 | 2022-10-30 06:43 | 100 | 2023-01-27 14:24 | 2023-02-24 14:24 |  | -
Learn Prolog Now! | Advanced Programming | 12 weeks | - | 100 | 2022-10-30 06:43 | 2022-11-27 06:43 | 100 | 2023-02-24 14:24 | 2023-03-24 14:24 |  | -
Software Debugging | Advanced Programming | 8 weeks | 6 hours/week | 48 | 2022-11-27 06:43 | 2022-12-10 17:17 | 48 | 2023-03-24 14:24 | 2023-04-07 00:58 |  | Python, object-oriented programming
Software Testing | Advanced Programming | 4 weeks | 6 hours/week | 24 | 2022-12-10 17:17 | 2022-12-17 10:34 | 24 | 2023-04-07 00:58 | 2023-04-13 18:14 |  | Python, programming experience
Final Project | Final Project |  |  | 100 | 2022-12-17 10:34 | 2023-01-14 10:34 | 100 | 2023-04-13 18:14 | 2023-05-11 18:14
Formulas:
Start Date = IF(ISBLANK([Actual End Date, row above]),[End Date Estimate Lower Bound, row above],[Actual End Date, row above])
Start Date = IF(ISBLANK([Actual End Date, row above]),[End Date Estimate Upper Bound, row above],[Actual End Date, row above])
End Date Estimate Lower Bound = IF(ISBLANK([Actual End Date]),[Start Date]+([Total Hours Lower Bound]/(Timeline!$B3/7)),[Actual End Date])
End Date Estimate Upper Bound = IF(ISBLANK([Actual End Date]),[Start Date]+([Total Hours Upper Bound]/(Timeline!$B3/7)),[Actual End Date])